## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Light
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Riku Nakano
Project start date: | 2024-05-12 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling increment: | 5 | time axis 2024-05-17 to 2024-07-11
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-17 to 2024-07-11
Project development
Project charter | Goal | Name | 25% | 2024-05-12 | 3
Research | Milestone |  |  | 2024-05-17 | 1 | bar: 2024-05-17
Projections | Low Risk |  | 50% | 2024-05-09 | 10
Stakeholders | Milestone |  |  | 2024-06-01 | 1 | bar: 2024-06-01
Review | Med Risk |  | 10% | 2024-05-18 | 6
Contracts
Proposals | High Risk |  | 60% | 2024-05-18 | 13
Document review | On Track |  | 50% | 2024-05-20 | 9
Bid date | Low Risk |  | 33% | 2024-05-25 | 11
Award date | Milestone |  |  | 2024-05-27 | 1 | bar: 2024-05-27
Finalize |  |  |  | 2024-05-28 | 24
Design
Feasibility study | On Track |  |  | 2024-05-27 | 4
Submit permit applications | Med Risk |  |  | 2024-05-30 | 14
Design proposal | On Track |  |  | 2024-06-14 | 6
Materials | Goal |  |  | 2024-06-18 | 3 | 2024-06-18: 2; 2024-06-19: 2; 2024-06-20: 2
Equipment | Low Risk |  |  | 2024-05-18 | 19
Testing
Environment |  |  |  | 2024-06-21 | 15
System test |  |  |  | 2024-07-05 | 5
Issues/bugs | Milestone |  |  | 2024-08-16 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT: Web-based mobile banking app
A website for Mobile banking app |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2024-05-12 |  |  |  |  | May | [20 empty] | June | [27 empty] | July | [41 empty] | August
scrolling increment | 1 | time axis 2024-05-13 to 2024-08-25
Column1 | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
initiation
Brainstorm the Idea | Goal | All 4 team members | 5% | 2024-05-12 | 3 | M: 2; T: 2
Ideintify the stakeholders | On Track | Abdi,Hussnain | 50% | 2024-05-10 | 1
identify the sponsor | Low Risk | All team members | 40% | 2024-05-17 | 1 | bar: F
project charter | Milestone | All team members | 50% | 2024-05-09 | 10 | bar: M to S
External review of project charter | Milestone | Hussnain | 40% | 2024-06-01 | 1 | bar: T; S
project charter approved | Med Risk |  | 10% | 2024-05-18 | 6
Planning
Requirements gathering and meeting workshops | Goal | All team members | 60% | 2024-05-18 | 13 | S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2
Reqquirements specifications approved | Milestone | Hussnain | 50% | 2024-05-20 | 9 | bar: T to T
Determine cost and time estimate | Goal | Ajay | 33% | 2024-05-25 | 11 | S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2
Budget Schedule approval | Milestone | Bappi | 20% | 2024-05-27 | 1 | bar: M
Quality managemnt plan approval | Milestone | Abdi,Hussnain | 40% | 2024-05-28 | 14 | bar: F to M
Execution
Front End,back-end Coding | Goal | Ajay,Abdi | 40% | 2024-05-27 | 24 | M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
Database design and development | Med Risk |  | 20% | 2024-05-30 | 14 | bar: S to S
implementing secured access control | Goal | Abdi | 60% | 2024-06-14 | 6 | F: 2; S: 2; S: 2; M: 2; T: 2; W: 2
System intergration and testing | Milestone | Abdi,Ajay | 10% | 2024-06-18 | 3 | bar: F to T
Launch website | Milestone | All team members | 15% | 2024-05-18 | 19 | bar: T to W
Monitoring and control
monitor and manage project team | Goal | Hussnain | 20% | 2024-06-21 | 15 | F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2; S: 2; S: 2; M: 2; T: 2; W: 2; T: 2; F: 2
prepare weekly status report | Low Risk | Hussnain | 20% | 2024-07-05 | 5
Monitor and manage scope,time and quality | Milestone | Hussnain,Abdi | 10% | 2024-08-16 | 1 | bar: F
monitor and manage stakeholders | Low Risk | Husnain | 25% | 2024-08-18 | 1 | bar: S
Closing
Handover,website,application and database | Milestone | All team members | 10% | 2024-08-20 | 1 | bar: T; T
Handover all the documents and documentation. | Goal | Husnain | 10% | 2024-08-21 | 2 | W: 2; T: 2
conduct final quality checks | Low Risk | Abdi,Ajay,Bappi | 9% | 2024-08-22 | 2
get the final sign-off | Goal | Husnain | 1% | 2024-08-26 | 1
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-05-12 |  |  |  |  | May | [20 empty] | June | [27 empty] | July
Scrolling increment: | 5 | time axis 2024-05-17 to 2024-07-11
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-17 to 2024-07-11
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-12 | 3
Task 2 | Milestone |  |  | 2024-05-17 | 1 | bar: 2024-05-17
Task 3 | Low Risk |  | 50% | 2024-05-09 | 10
Task 4 | Milestone |  |  | 2024-06-01 | 1 | bar: 2024-06-01
Task 5 | Med Risk |  | 10% | 2024-05-18 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-18 | 13
Task 2 | On Track |  | 50% | 2024-05-20 | 9
Task 3 | Low Risk |  | 33% | 2024-05-25 | 11
Task 4 | Milestone |  |  | 2024-05-27 | 1 | bar: 2024-05-27
Task 5 |  |  |  | 2024-05-28 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-05-27 | 4
Task 2 | Med Risk |  |  | 2024-05-30 | 14
Task 3 | On Track |  |  | 2024-06-14 | 6
Task 4 | Goal |  |  | 2024-06-18 | 3 | 2024-06-18: 2; 2024-06-19: 2; 2024-06-20: 2
Task 5 | Low Risk |  |  | 2024-05-18 | 19
TITLE 4
Task 1 |  |  |  | 2024-06-21 | 15
Task 2 |  |  |  | 2024-07-05 | 5
Task 3 | Milestone |  |  | 2024-08-16 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one